## Communication Plan
Stakeholder | What | When | How | Who | Where
Health Department | Safety measures included in the project plan | Before campaign | Online/In-person | Team Valor | Email/Zoom/Webex/Office
| Covid-19 guidelines | Before/During campaign | Online/In-person | Team Valor | Email/Zoom/Webex/Office/Campaign locations
Team Members | Time and days are the team members meeting | During the project | Phone | Team Valor | Whatsapp Group
| Status of project | During the project | Weekly Meetings/Phone | Team Valor | Whatsapp Group/Webex
| Status of campaign | During the campaign | Phone/In-person | Team Valor | Whatsapp/Call/Campaign Location
Campaign Team Members | Campaign timings and location | Before/During campaign | Phone/In-person | Team Valor | Call/Text/Email/Campaign locations
| Roles in detail | Before the campaign | Online/In-person | Team Valor | Email/Zoom/Webex
Location Partners | Location requirements | Before the campaign | Online/In-person | Team Valor | Email/Zoom/Webex/Campus
| Capacity Requirements | Before/During campaign | Online/In-person | Team Valor | Email/Zoom/Webex/Campus
| Budegt Estimate | Before the campaign | Online/In-person | Team Valor | Email/Zoom/Webex/Campus
Professor | Status of project | During the project | Online | Team Valor | Weekly Webex
| Issues on the project | During the project | Online | Team Valor | Email/Webex
Business Organizations | Marketing strategy | Before the campaign | Online/In-person/Application on their website | Team Valor | Email/Webex/Marketing company office/Website
| Technology Requirements | Before/During campaign | Online/In-person/Application on their website | Team Valor | Email/Webex/Tech company office
| Communications languages | Before the campaign | Online/In-person/Application on their website | Team Valor | Email/Webex/Translation company Office/Website
| Staff Requirements | Before the campaign | Online/In-person/Application on their website | Team Valor | Email/Webex/Staffing company Office/Website
| Insurance details | Before the campaign | Online application | Team Valor | Insurance company website
| Budget Estimate | Before the campaign | Email/In-person | Team Valor | Email/Webex/Zoom/Office
Investors/Fundraising | Impact on the underserved community | On April 28th, 2021 at 6:00 pm | Project Presentation | Team Valor | Webex
| Covid-19 awareness | On April 28th, 2021 at 6:00 pm | Project Presentation | Team Valor | Webex
| Capital requirements | On April 28th, 2021 at 6:00 pm | Project Presentation | Team Valor | Webex
Suppliers(Education Material) | Vaccine related information | Before the campaign | Online/In-person | Team Valor | Email/Zoom/Webex/Rutgers Campus
Medical Organizations | Education | Before/During campaign | Online/In-person | Team Valor | Email/Campaign Locations
| Awareness | Before/During campaign | Online/In-person | Team Valor | Email/Campaign Locations
Target Audience | Information related to covid-19 vaccination | Before/During campaign | Online/Call/In-person | Team Valor/Staff/Volunteers | Email/Phone/Campaign Location
| Complaints | Before/During campaign | Online/Call/In-person | Team Valor/Staff/Volunteers | Email/Phone/Campaign Location
| Authenticity | Before/During campaign | Online/Call/In-person | Team Valor/Staff/Volunteers | Email/Phone/Campaign Location